## SOW
Label | Description | Start Month
Data Modeling & Knowledge Extraction
DM-01: Data Repository | Establish centralized, standardized FAIR data repository. | 1
MS-01: Microbial Selection | Select candidate strains for bioprocessing applications. | 2
KE-01: Literature extraction | Extract knowledge from CMM-REE literature corpus. | 1
KE-02: Knowledge Graph Dev | Build knowledge graph from project and public data. | 4
Model Training & Evaluation
MT-01: ML Model Dev | Develop supervised ML models for phenotype prediction. | 1
ME-01: Model Validation | Rigorously validate models against held-out experimental data. | 3
ME-02: Model Refinement | Refine models with new spectroscopic and phenotype data. | 4
Model Inference & Explanations
MI-01: Driver Gene ID | Suggest and interpret key driver genes. | 6
MI-02: Digital Twin Build | Integrate models into a comprehensive "digital twin" simulation. | 7
MI-03: KG Reasoning Engine | Deploy AI reasoning engine to query knowledge graph and data. | 8
MI-04: ART Parameter Rec | Recommend the chemical space and parameters for the ART tool. | 9
MI-05: In Silico Evolution | Suggest and interpret strain designs. | 9
MI-06: Hypothesis Generation | Automatically generate novel, systems-level hypotheses for testing. | 11
MI-07: Design Delivery | Rank and deliver AI-generated strain designs to experimental team. | 12

## Action plan
Task | Who | When
identify literature collection | LBLCMM
extract knowledge from literature | MAM, MPJ
add it to KG-Microbe framework | MAM, MPJ
identify datasets from DOE collection and literature | LBLCMM
identify metagenome and other biosamples | LBLCMM
process and prepare data with reproducible process | LBLCMM + MAM, MPJ + NMDC + KBase
based on data surveys match to possible method and models
graph transformer for KG-CMMREE is ready

## Interactions
| ET 1: Strain Engineering | ET 2: Bioprocess Validation | ET 3: Molecular Characterization | ET 4: Biochemical Assays | ET 5: Phenotyping
AI WP 1: Predictive Phenotype Modeling | Provides predictions for engineered strain performance to guide design choices. | Uses bioprocess data for model validation at scale. | Provides context for interpreting gene expression changes. | Uses kinetic data to parameterize mechanistic models (GEMs). | INPUT: Consumes high-throughput data for model training and validation.
AI WP 2: Multi-Omics Integration | Receives engineered strains for 'omics' analysis. | Provides systems-level explanation for bioprocess outcomes. | INPUT: Consumes transcriptomic/proteomic data for network inference. OUTPUT: Delivers novel gene targets for validation. | Provides functional context for newly identified proteins. | Correlates gene networks with specific phenotypes.
AI WP 3: AI-Guided Strain Design | OUTPUT: Delivers ranked, multi-gene engineering strategies for implementation. | Defines the objective function (e.g., maximize yield) for in silico evolution. | Identifies key regulatory nodes to target for engineering. | Provides performance parameters for the "digital twin" model. | Predicts phenotypes of novel, untested genetic designs.
AI WP 4: Knowledge Synthesis | Integrates engineering outcomes into a project-wide knowledge base. | Links bioprocess performance to community-level ecological models. | INPUT: Consumes all 'omics' data. OUTPUT: Generates novel, systems-level hypotheses for testing across scales. | Integrates enzyme data into a broader biological context. | Connects single-organism phenotypes to multi-species interaction models.